## NAR Samruddi
NAR Samruddi- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Feasibility study of Fractional Investment | Analyze the demand for fractional ownership in commercial real estate.
Understand & ascertain the regulatory landscape governing fractional ownership in real estate, especially in TN.
Evaluate the availability of technology infrastructure for secure transactions, transparent reporting, and a user-friendly experience.
Develop legal frameworks, property valuation methods, and contingency plans for unforeseen events.
Consider the liquidity of the investment wrt the potential challenges associated with liquidity in the real estate market.
Focus on creating an intuitive and user-friendly platform.
Due Diligence in terms of Transparency in property details, financials, and potential risks is crucial for building trust among investors.
Process for establishing for strong partnerships with stakeholders can contribute to a diverse and attractive portfolio for potential investors.
Provide clear exit strategies for investors, including options to sell their fractional shares or exit the investment at predefined intervals.
Analyze existing and potential competitors in the market. Differentiation and innovation will be essential to stand out in a competitive landscape.
Consider the economic climate and its impact on commercial real estate. Economic downturns or uncertainties can affect property values and rental incomes.
Budgeting/ AOP | Review of 23-24 and finalization of Budgeting for 24-25

## DAC Developers
DAC Developers- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
GIO Goals and AOP Reviews & Completion | AOP launch, setting expectations, discussing key people involvement and finalizing the plan
Sharing the formats, data requirement with different functions for data
Sending list of Required Details in the particular format
Receipt of details from Client's team
Preparation of AOP
First Cut AOP Submission and Discussion
Working on required changes after first discussion
Finalisation of AOP
Final Presentation
Implementation plan
Working Groups & Commitee Goals / KPIs | Review the current processes how decisions are taken currently; Land purchase, Design & Structural, Vendors appointment for Material Supplies, Marketing Services and Other Admin Services, Project Scheduling, IT H/W & S/W Purchases, etc.
Identify the gaps if any in the current processes for informed decision making
Define which are all functions must be involved in decision making for each such activity
Form separate work group committes for each such activity
Define the process of decision making by the committee
Align all stake holders including top management on the WC process
Monitor the implementation through periodic internal review
Finance & Purchase SOP | Align the respective team with the draft SOP
Finalize the SOP after feedback from all stakeholders
Share the SOP with the respective functions for implementation
Monitor the implementation through periodicreview of internal audit plans and reports
Construction Site process | Awaiting Engineering SVP feedback/inputs
Roll out to Site Teams

## Kamala Farms
Kamala Farms- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
AOP Preparation, Review and Completion | AOP launch, setting expectations, discussing key people involvement and finalizing the plan
Sharing the formats, data requirement with different functions for data
Sending list of Required Details in the particular format
Receipt of details from Client's team
Preparation of AOP
First Cut AOP Submission and Discussion
Working on required changes after first discussion
Finalisation of AOP
Final Presentation
Implementation plan
Articulation of Business Critical Goals / KPIs | Identify business critical goals for the year
Identify the critical KPIs to be delivered against each of these goals
Identify timelines for delivery of each of these goals
Align the senior management and founders
Make changes based on the discussion with the founders and senior management
Finalise the goals and start the implementation process
Extraction Plant Readiness | Prepare Tracker for all the requirements
Follow up on required licenses for setting up the plant
GST Registration
Follow up on bank loan sanction
Track Procurement of Plant & Machinery required and Installation
Procurement of Input Materials and Initial sample batches for commercial clearance
ROI Working
Essential Oils Readiness | Prepare Tracker for all the requirements
Follow up on required licenses for setting up trading
GST Registration
Amazon Listing
Track Procurement of purchases
Review and Finalise the pricing
ROI Working

## VC Nutri Foods
VC Nutri Foods- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
AOP Preparation, Review and Completion | AOP launch, setting expectations, discussing key people involvement and finalizing the plan
Sharing the formats, data requirement with different functions for data
Sending list of Required Details in the particular format
Receipt of details from Client's team
Preparation of AOP
First Cut AOP Submission and Discussion
Working on required changes after first discussion
Finalisation of AOP
Final Presentation
Implementation plan
Articulation of Business Critical Goals / KPIs | Identify business critical goals for the year
Identify the critical KPIs to be delivered against each of these goals
Identify timelines for delivery of each of these goals
Align the senior management and founders
Make changes based on the discussion with the founders and senior management
Finalise the goals and start the implementation process
Cash Flow Forecasting & Management | Cash Flow forecasting and management
Template for Weekly and Monthly Cash flow forecasting and management
Cash flow forecasting (to anticipate any potential shortfalls or surpluses)
Track the actual cash inflow and outflow against the forecasted no.
Align and Fix payment days for vendors, salary and reimbursement
Review the payment terms with vendor and suggest improvements
Receivable management through well defined follow up system and process
Advise on effectively managing cashflow shortfalls and excess
Three months rolling cash flow forecast every month
Monthly P&L Process | Review current Monthly P&L process
Ensure Cut Off Dates for Month Closing
Ensure Month End Provisioning for all unbooked bills/expenses
All Production Orders are confirmed by month end ensure material consumption accounting
Month End Physical Verification for FG, SFG and RMPM Inventory
Monthly P&L Closure and Output
P&L Analysis, insights and action plans
Sustain Monthly & YTD P&L process

## Crossasyst
Crossasyst- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Finalisation of MIS for FY 23-24 and review the same | Drive closure of books
Gather all the informations from the account team
Create MIS for the FY including PnL, BS and Cash flow
Implementation of Record to report SOP
Management Information Systems | Submission of Monthly Business Deck
Monthly Business Review
Project Wise Costing and Profitability working
Compliance Checklist
Other Finance related deliverables | Marketing- monitoring the leads and conversion through participation in the calls
Monitoring the lost of billing due to leaves and holidays on a monthly basis
Finalisation of Incentive for new Sales Head

## Balaji Food Products
Balaji Food Products- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Inventory optimization | Inventory reconciliation and compiling Non-moving items across multiple units.
Monitoring non-moving items across units and implementing disposal procedures along with timelines
Monthly MIS Update & deck | Monthly update: PnL, CFS, BS on MoM basis, followed by consolidated MIS.
Creation of Monthly Performance deck for all units
Monitoring Major KPI, Variance Analysis
Reconciliation of outstanding amounts in all the branches.
Annual Event | Review of last year's business performance, highlighting constraints with the sales, production, and accounts teams, and proposing a way forward.
Drafting meeting minutes and highlighting forward-thinking suggestions.
Sales & Production planning and Alignments | Annual Operating Plan (AOP) Discussion with Management
Detailed planning for major SKUs in volume terms for production across all units.
Aligning production with sales targets for each sales region.
Cash Flow Analysis | Cash Flow Analysis and Discussion for Each Business Unit, along with a Consolidated View for Management Review
Rolling forecast and AOP Update | Update the Annual Operating Plan (AOP) for each business unit in accordance with the revised sales and production targets for the first and second quarters.
Petty cash monitoring protocol. | Analyzing significant petty cash outflows and mitigating potential leakages through effective measures.
Implementing a standardized procedure for cash disbursements and payments within the business.
Brand building and marketing analysis. | Analyzing new sales channel of D2C and modern trade sales segment with a cost-benefit analysis for marketing and sales.
Inventory Management | Updating BoM of Major Products and Contribution Margin workings as per new BoM
Implement a weekly update of material issues to production, including weekly adjustments and ensuring Bill of Materials (BoM) accuracy in line with prevailing trends.
Develop Sops for Inventory dispatch procedures
Cost Optimizations | Conducting a comparative cost analysis and benefits evaluation between bag packaging and carton box packaging.
Computation of yields at the plant level to optimize and enhance operational efficiency.
Closely monitoring major P&L items for effective operational cost reduction.
Analyzing slow-moving items at the Ranchi Plant and formulating a production plan based on historical demand patterns.

## SL7
Sl7- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Weekly Dashboard Monthly Closing Activity and Performance Review | Weekly Dashboard submission by every Tuesday of nect week
Drive timely closure of books
Preparation of Monthly Business Review Deck
Monthly Business Review with the founder in the first week of every month
Cash Flow and Wealth Management | Monitoring the returns on investment on weekly basis to achieve the target of 8% p.a
Quarterly review with the wealth advisor
Cash flow forecasting and monitoring the collections through weekly cadence calls
Compliances | Timely Delivery of Compliance Checklist with Zero Non Compliance on a monthly basis
Accurate calculation and timely payment of advance tax
US Compliance- Annual and Monthly
Financial Processes | Pricing Strategy
ROI on all marketing spends
Assistance in Zoho Books Finalization and Audit | Assist in Accounting and Book closing
Zoho ERP Support
Audit coordination and Support

## Vervali
Vervali- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Organisational Goal under Balanced score Card | - From financial perspective
- From Customer perspective
- From Internal Processes perspective
- From Learning & Growth perspective
Discussion and finalisation with the Management
Annual Operating Plan Implementation | - Set clear and measurable Organisation objective aligned with AOP
- Communication to the functional heads and alignment with their individual goal sheets
- Set targets and Budgets for each department and business units
- Allocate Budgets to individual departments
- Align Capability building Budgets with the respective functions
- AOP refresh at the end of quarter (if required)
Management Information Systems | Submission of Monthly Business Deck
Project Wise Costing and Profitability working
Fornight Call with the Leadership team with clear actionables
Monthly Review with all functions
Monthly Business Review

## Incertech
Incertech- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Cost and Pricing | Live google sheet created for Costing and Pricing
SOP and process flows drafted to define each and every stage create the sheet
Implementation of pricing sheet
Record to Report | Driving closure of accounting for last FY
Improvement and Discipline in accounting processes
Drafting R2R Policies to drive the accounting systems better
Streamlining accounting and MIS systems
Monthly MIS | Introduction of monthly business review deck after aligning on KPIs required to monitor on monthly basis
Introduction of monthly business review with key stakeholders

## Tataria Group
Tataria Group- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Weekly and Daily Dashboard | Improvisation and Implementation of Weekly dashboard for Ligno Industries
Improvisation and Implementation of Weekly dashboard for Tataria Living
Cash Flow Management | Cash Flow Forecasting and Management for Ligno Industries
Cash Flow Forecasting and Management for Tataria Living
Cash Flow Forecasting and Management for Tataria Hardware
Monthly MIS | Proper monthly Management Information System for Ligno Industries
Proper monthly Management Information System for Tataria Living
Proper monthly Management Information System for Tataria Hardware
Monthly Business Performance review | Drive the Monthly Business Performance review for Ligno Industries
Drive the Monthly Business Performance review for Tataria Living
Drive the Monthly Business Performance review for Tataria Hardware
Standard Operating Procedure | Procure to Pay SOP - for Ligno Industries
Drive the processes of Inventory forecasting in Tataria Hardware

## Agos Aviation
Agos Aviation- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Weekly and Daily Dashboard | Understand the requirement and define the KPIs to be included in Daily and Weekly Dashboard
Create a dashboard and discuss the same with management
Finalisation and implementation of Dashboard
Monthly MIS | Create and improvise the MIS to include the cash flow and reconciliation with the books
Creation of monthly business performance deck and implementation of the same
Drive and implement the monthly performance review with the key stakeholders
Debtor Management System | Prepare tracker from trade receivables with aging schedule and Streamline the process of collection
Payment Mechanism System | Implement proper process and control for making payments
Cash Flow Management | Implement cash Flow tracker for payment and collection
Standard Operating Procedure | SOPs for Cash
Other deliveries | Renegotiation with CMACGM and finalisation of quote
Workings done for 3 scenarios- without ACS, Inditex and ACS & Inditex

## LFT
LFT- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Implementation of AOP | Finalize the AOP with the appropriate building blocks and assumptions
Set clear and measurable Organisation objective aligned with AOP
Communication to the functional heads and alignment with their individual goal sheets
Set targets and Budgets for each department and business units
Allocate budgets to individual departments
Align Capability building budgets with the respective functions
Discuss and define the capabilities required for winning - resources, funds, tools, technology etc
Continuous Monitoring and review progress
AOP refresh at the end of quarter (if required)
Finalizing Airtable for Revenue Tracking | Testing Airtable for Finalizing the model of RTS Data capture including identifying all the pros and cons of Airtable as a revenue management tool to ensure better visibility
Assess potential limitations or challenges of Airtable, such as scalability issues or integration constraints and Analyze how Airtable's features align with the specific needs of revenue management, considering factors like data visualization and reporting capabilities.
Compile a comprehensive list of pros and cons based on the evaluation, highlighting key points for decision-making.
RTS Dashboard | Develop the data model required for the RTS dashboard.
Create mock data and conduct initial testing of the dashboard functionality.
Finalize the dashboard design and publish it to stakeholders for feedback.
Project R&D Sheet-MIS Project Costing Sheet Prepare Project Financial Sheet | Schedule a meeting with ERP vendor to discuss requirements for capturing revenue department-wise data and Provide detailed specifications and data format needed for the customization.
Review and approve the proposed solution from the ERP vendor and drive the testing the implemented solution for accuracy and functionality.
Arrange a meeting with the GreytHR team to discuss requirements for capturing EOS information And Provide necessary documentation and guidelines for the integration of EOS Data within the system.
Review the proposed customization from the GreytHR team
Test the implementation to ensure accurate capture of EOS information and provide feedback for adjustments (if any)
Documentation of the requirements, specifications, and implementation details should be maintained for future reference and troubleshooting.
Dashboard-Power BI | Data Connection & Transformation: Establish live connections in Power Query for all identified data sources (ERP, EOS Sheet, RTS)
Clean & Transform Data: Clean inconsistencies, format data types, and create calculated columns for profitability metrics (Revenue - Salary Cost - R&D Cost).
Building the Data Model & Dashboard Design : Define Relationships: Set up relationships between tables in the Power BI data model based on common fields
Design Dashboard Layout: Plan the layout for key insights: customer list, revenue, cost & profitability chart, fund flow chart, slicers & filters
Create Visuals: Use Power BI visuals to represent data - tables for customer lists, charts for profitability & fund flow trends.
Formatting & Branding: Apply consistent formatting throughout the dashboard for a visually appealing presentation aligned with your brand.
Test Functionality: Thoroughly test the dashboard for data accuracy, refresh functionality, and proper filtering/slicing behavior.
Schedule a review meeting with client stakeholders to assess the effectiveness of the Dashboard
Construct Scheduled workflows for automation of data refreshes and reporting for all stakeholders
Cashflow forecasting process and management | Forecasting Future cash inflows and outflows accurately
Drive the Implementation strategies to manage and optimize cash flow
Develop compliance checklist for the year to avoid penalty | Develop a comprehensive compliance checklist that governs Tax compliance, Regulatory compliance and other financial reporting compliance
Management Routines | Develop the weekly and monthly management routines Templates and drive their implementation
Prepare Finance Data – (Slides to be replaced by Dashboard-Power BI) & Loan Sheet Evaluation | Connect to data sources (RTS, ERP, AOP, Loan Sheet) and clean/transform data.
Build data model, define relationships, and design dashboard layout with KPIs, charts, and filters.
Create visualizations (line, bar, pie charts) and apply consistent formatting
Evaluating the possibilities of whether loan sheet can be automated
Identifying the relationship between different variables of the loan sheet
Build data model, define relationships, and Incorporating Loan sheet details into the dashboard
Test dashboard functionality, deploy to Power BI service or publish for local access.
Schedule a review meeting with client stakeholders to assess the effectiveness of the Dashboard
Based on the review meeting, refine the dashboard as required
Construct Scheduled workflows for automation of data refreshes and reporting for all stakeholders
Define the project costing and profitability process and templates | Estimate project costs with a Cost Estimation Worksheet.
Create a Project Budget Template to allocate resources effectively.
Use an Expense Tracking Sheet to monitor and control project expenses.
Assess project profitability with a Profitability Analysis Report.
GTM Strategy | Understand the market, customers, and competitors through market analysis
Define Value Proposition and Identifying the ideal customers .
Choosing the right channels and pricing strategy to reach your audience.
Develop marketing, sales, and launch plans, measure results, and adjust accordingly
Develop the P2P SOP | Develop a detailed SOP outlining each step of the procure-to-pay process
Review the SOP with relevant stakeholders to ensure clarity and accuracy.
Train employees on the SOP and drive the implement it across the organization.
Develop the R2R SOP | Develop a detailed SOP outlining each step of the record -to- report process
Review the SOP with relevant stakeholders to ensure clarity and accuracy.
Train employees on the SOP and drive the implement it across the organization.
Develop the O2C SOP | Develop a detailed SOP outlining each step of the order to cash process
Review the SOP with relevant stakeholders to ensure clarity and accuracy.
Train employees on the SOP and drive the implement it across the organization.
Develop the DOG SOP | Develop a detailed SOP outlining each step of the delegation of authority process
Review the SOP with relevant stakeholders to ensure clarity and accuracy.
Train employees on the SOP and drive the implement it across the organization.
Quarterly Business Review | Define functional reviews and calendarize them
Define the MIS And dashboards to be reviewed by each functions
Create actionables and responsibilities out of review
Evaluate next quarter's target and make changes if required
Communicate the targets to the relevant functions
Analyse and communicate the quarterly targets with all functions

## Maven
Maven Sillicon- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Accounting Support | Ensuring accurate recording of financial transactions such as Chart of accounts setup, recording transactions (sales, purchases, receipts, payments), bank reconciliations | X | X | X | X | X | X | X | X | X | X | X | X
| Continous rigour around regulatory changes and ensuring compliance. | X | X | X | X | X | X | X | X | X | X | X | X
| Reviewing transactions and determining the appropriate TDS sections and rates. | X | X | X | X | X | X | X | X | X | X | X | X
| Calculating and posting prepaid expenses. | X | X | X | X | X | X | X | X | X | X | X | X
| Posting provisional entries for expenses incurred during the current period. | X | X | X | X | X | X | X | X | X | X | X | X
| Managed GST compliance and recorded GST set-off entries. | X | X | X | X | X | X | X | X | X | X | X | X
| Validation of Advance Tax | X | X | X | X | X | X | X | X | X | X | X | X
| Recording salary entries with comprehensive breakdowns, ensuring alignment with the net payable amount. | X | X | X | X | X | X | X | X | X | X | X | X
| Ensuring statutory compliance in the books, including PF, PT, and ESI. | X | X | X | X | X | X | X | X | X | X | X | X
| Provided a detailed explanation of indirect and direct revenue, segregating according to the Annual Operating Plan (AOP). | X | X | X | X | X | X | X | X | X | X | X | X
| Treatment of Electricity expenses - Recording electricity expenses as a debit note and deducting them from the P&L electricity expenses. | X | X | X | X | X | X | X | X | X | X | X | X
| Accurate recording of interest on a periodic basis and ensuring reconciliation with loan statements. | X | X | X | X | X | X | X | X | X | X | X | X
| Equipping the accountant with skills to prepare accurate financial statements. | X | X | X | X | X | X | X | X | X | X | X | X
| Ensuring to file the return with relevant tax laws and regulations. | X | X | X | X | X | X | X | X | X | X | X | X
| Implementing and maintaining effective internal controls and preparing for audits. | X | X | X | X | X | X | X | X | X | X | X | X
| Monthly depreciation provision and working with respect to capex | X | X | X | X | X | X | X | X | X | X | X | X
| Compliance with R2R/P2P/O2C SOP | X | X | X | X | X | X | X | X | X | X | X | X
Strategy & Financial Planning | Financial Benchmarking- Cost savings plan |  |  | X
| Sales Pipeline Review- Alignment with Q2 Targets |  |  | X |  |  |  | X
| ROI Marketing Spends |  |  |  | X |  |  |  | X
| Global Strategy - New Product & International Expansion |  |  |  | X
| Cash Flow Forecasting - Actual vs Plan |  |  | X |  |  |  | X |  |  |  | X
| Debt Repayment Planning |  |  |  |  | X
| Monthly Financial Review- P&L | [5 empty] | X |  |  |  |  | X
| Quarterly Balance Sheet & Cash flow analysis | [5 empty] | X |  |  |  | X
| Ratio Analysis Dashboard: Key Financial Ratios¦Profitabillity /Balance Sheet etc | [5 empty] | X |  |  |  | X
| Evaluate Capex Requirements, funding requirements | [5 empty] | X |  |  |  | X
Compliance Risk Evaluation | Conduct evaluation of ALL legal notices |  |  |  | X
| Firm-up and finalise the compliance checklist basis the compliance risk evaluation |  |  |  |  | X
Tax Evaluation | Evaluate tax payouts , oppurtunities for tax planning etc |  |  |  | X
Goals/KPIs | Goal Sheet Formulation and progress evaluation ( Quarterly Evaluation) |  |  |  | X
Quarterly Business Review | Detailed Business & Financial Review with MD/Business Heads | [7 empty] | X
Systems & ERP Implementation | Monitor the implementation of customization of tally by the Implementation partner | [6 empty] | X
Service Delivery Meeting | Monthly service delivery meeting with Praveena | [7 empty] | X |  |  |  | X

## Agriplast
Agriplast- 90 Days Plan ( Weekly Plan)
Focus Area | Task | June |  |  |  | July |  |  |  | Aug
|  | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 30th Aug
Financial Process Review | Financial Forecast launch, setting expectations, discussing key people involvement and finalizing the plan and calendar
Sharing the formats, data requirement with different functions for data
Receipt of details from Client's Team
Preparation of Financial Forecast
First Cut Finnacial Forecast Submission and Discussion
Finalize the AOP with the required changes after first discussion
Start the implementation & share the finalized KPIs to all functions
Financial Forecast | Financial Forecast launch, setting expectations, discussing key people involvement and finalizing the plan and calendar
Sharing the formats, data requirement with different functions for data
Receipt of details from Client's Team
Preparation of Financial Forecast
First Cut Finnacial Forecast Submission and Discussion
Finalize the AOP with the required changes after first discussion
Start the implementation & share the finalized KPIs to all functions
Annual Operating Plan | AOP launch, setting expectations, discussing key people involvement and finalizing the plan and calendar
Sharing the formats, data requirement with different functions for data
Receipt of details from Client's Team
Preparation of AOP
First Cut AOP Submission and Discussion
Working on required changes after first discussion
Finalisation of AOP and presentation
Start the implementation & share the finalized KPIs to all functions
Detailed Finance Diagnostics | Session with the Key Management Team (KMT) on finance related challenges & expectations
Structured / Unstructured diagnostics on Internal controls,SOPs, MIS, key challenges, issues in finance function
Review and analyse existing Financials for growth tends and key financial ratios
Conduct the Finance baseline assessment along with Finance team and highlight gap areas if any
Creating a business diagnostics report based on the findings
Report presentation to the founders
Procure to Pay SOP | Review the current process (documented / undocument) of procure to pay from the Procurement team, Stores / warehouse team and Finance team
Evaluate the process for financial controls i.e. segregation of duties, maker, checker control, reconciliation control et all
Identify the gaps and script the revised SOP with deliverables defined for each function involved
Share the draft SOP with the management team for approval / feedback
Share the final SOP post incoporating the feedback received from the management
Implement the SOP with the support of Procurement, stores / warehouse and finance team
Order to Cash SOP | Review the current process (documented / undocument) of Order to Cash from the Sales / Post salest team, Stores / warehouse team and Finance team
Evaluate the process for financial controls i.e. segregation of duties, maker, checker control, reconciliation control et all
Identify the gaps and script the revised SOP with deliverables defined for each function involved
Share the draft SOP with the management team for approval / feedback
Share the final SOP post incoporating the feedback received from the management
Implement the SOP with the support of Sales / Post salest team, Stores / warehouse team and Finance team
Cashflow forecast and Wealth Management | Understand the current process on cashflow management and forecast. How is the forecast created ? Is it weekly, monthly?
Share the format for cashflow forecast, data requirement with different functions for data (Weekly, monthly)
Train the finance team on creation of Cash flow forecasts and more importantly manage the cashflows on weekly basis
Monitor the cashflows on a weekly, monthly basis for improvement in net cashflow
Montior the actauls vs forecast on a weekly basis to improve the forecasts
Ensure the periodic surplus funds are invested in funds / FDs
Monitor the returns from the surplus funds invested every month
Compliance Management | Customize the compliances checklist based on the compliances to be done & monitored periodically. Share the same with Finance Team
Finalize the checklist based on feedback from the Finance Team
Ensure that the checklist is updated everymonth before the payment and filing due dats
The udpated checklist is reveiwed every month with the Finance team
Once a quarter review with the management onstatus of complainces for the last quarter
Incase of any delays or defaults, define actionables to ensure no delays or defaults in the future
Record to Report SOP | Review the current process (documented / undocument) of record to report process with the Finance Team
Evaluate the process for financial controls i.e. segregation of duties, maker, checker control, reconciliation control et all
Identify the gaps and script the revised SOP with deliverables defined for each function involved
Share the draft SOP with the management team for approval / feedback
Share the final SOP post incoporating the feedback received from the management
Implement the SOP with the support of Sales / Post salest team, Stores / warehouse team and Finance team
Create a month end closing checklist to ensure accurate MIS for each month from SAP
Monthly Performance Review | Monthly and YTD financial performance review

## West (hidden)
FlipCarbon- CFO ¦Delivery Tracker | [6 empty] | April |  | May |  | June |  | Remarks
Engagement Name | Engagement Type | Region | Periodicity | Focus Area | Task | Assigned To | Due Date | Status | Due Date | Status | Due Date | Status
Agos Aviation | Business Consulting | West | One-time | Weekly and Daily Dashboard | Understand the requirement and define the KPIs to be included in Daily and Weekly Dashboard | Hina |  |  | 4th Week of May | Work-in-progress
Agos Aviation | Business Consulting | West | One-time | Weekly and Daily Dashboard | Create a dashboard and discuss the same with management | Ghanisht |  |  | 4th Week of May | Not Started
Agos Aviation | Business Consulting | West | One-time | Weekly and Daily Dashboard | Finalisation and implementation of Dashboard | Ghanisht |  |  | 4th Week of May | Not Started
Agos Aviation | Business Consulting | West | One-time | Monthly MIS | Create and improvise the MIS to include the cash flow and reconciliation with the books | Ghanisht | 4th Week of April | Completed
Agos Aviation | Business Consulting | West | Monthly | Monthly MIS | Creation of monthly business performance deck and implementation of the same | Ghanisht |  |  | 3rd Week of May | Work-in-progress
Agos Aviation | Business Consulting | West | Monthly | Monthly MIS | Drive and implement the monthly performance review with the key stakeholders | Ghanisht |  |  | 2nd Week of June | Work-in-progress | 2nd Week of June | Not Started
Agos Aviation | Business Consulting | West | One-time | Debtor Management System | Prepare tracker from trade receivables with aging schedule and Streamline the process of collection | Ghanisht |  |  | 1st Week of June | Work-in-progress | 1st Week of June | Work-in-progress
Agos Aviation | Business Consulting | West | One-time | Payment Mechanism System | Implement proper process and control for making payments | Ghanisht |  |  |  |  | 3rd Week of June | Not Started
Agos Aviation | Business Consulting | West | One-time | Cash Flow Management | Implement cash Flow tracker for payment and collection | Ghanisht |  |  |  |  | 1st Week of June | Not Started
Agos Aviation | Business Consulting | West | One-time | Standard Operating Procedure | SOPs for Cash | Ghanisht |  |  |  |  | 4th week of June | Not Started
Agos Aviation | Business Consulting | West | One-time | Other deliveries | Renegotiation with CMACGM and finalisation of quote | Hina | 4th Week of April | Completed
Agos Aviation | Business Consulting | West | One-time | Other deliveries | Workings done for 3 scenarios- without ACS, Inditex and ACS & Inditex | Ghanisht | 2nd Week of April | Completed
Tataria Group | Business Consulting | West | One-time | Weekly Dashboard | Improvisation and Implementation of Weekly dashboard for Ligno Industries | Ghanisht | 3rd Week of April | Completed
Tataria Group | Business Consulting | West | One-time | Weekly Dashboard | Improvisation and Implementation of Weekly dashboard for Tataria Living | Ghanisht | 1st Week of May | Completed | 1st Week of May | Completed
Tataria Group | Business Consulting | West | Monthly | Cash Flow Management | Cash Flow Forecasting and Management for Ligno Industries | Ghanisht | 1st Week of May | Completed | 1st Week of May | Completed
Tataria Group | Business Consulting | West | Monthly | Cash Flow Management | Cash Flow Forecasting and Management for Tataria Living | Ghanisht |  |  | 3rd Week of May | Work-in-progress
Tataria Group | Business Consulting | West | Monthly | Cash Flow Management | Cash Flow Forecasting and Management for Tataria Hardware | Ghanisht | 4th Week of April | Completed
Tataria Group | Business Consulting | West | Monthly | Monthly MIS | Proper monthly Management Information System for Ligno Industries | Ghanisht |  |  |  |  | 2nd Week of June | Not Started
Tataria Group | Business Consulting | West | Monthly | Monthly MIS | Proper monthly Management Information System for Tataria Living | Ghanisht |  |  |  |  | 2nd Week of June | Not Started
Tataria Group | Business Consulting | West | Monthly | Monthly MIS | Proper monthly Management Information System for Tataria Hardware | Ghanisht |  |  |  |  | 2nd Week of June | Not Started
Tataria Group | Business Consulting | West | Monthly | Monthly Business Performance review | Drive the Monthly Business Performance review for Ligno Industries | Ghanisht |  |  |  |  | 2nd Week of June | Not Started
Tataria Group | Business Consulting | West | Monthly | Monthly Business Performance review | Drive the Monthly Business Performance review for Tataria Living | Ghanisht |  |  |  |  | 2nd Week of June | Not Started
Tataria Group | Business Consulting | West | Monthly | Monthly Business Performance review | Drive the Monthly Business Performance review for Tataria Hardware | Ghanisht |  |  | 2nd Week of June | Work-in-progress | 2nd Week of June | Not Started
Tataria Group | Business Consulting | West | One-time | Standard Operating Procedure | Procure to Pay SOP - for Ligno Industries | Hina |  |  |  |  | 4th Week of June | Not Started
Tataria Group | Business Consulting | West | One-time | Standard Operating Procedure | Drive the processes of Inventory forecasting in Tataria Hardware | Hina |  |  |  |  | 4th Week of June | Not Started
Incertech | CFO | West | One-time | Costing and Pricing | Live google sheet created for Costing and Pricing | Ghanisht | 3rd Week of April | Completed
Incertech | CFO | West | One-time | Costing and Pricing | SOP and process flows drafted to define each and every stage create the sheet | Hina | 3rd Week of April | Completed
Incertech | CFO | West | One-time | Costing and Pricing | Implementation of pricing sheet | Ghanisht | 4th Week of May | Work-in-progress | 4th Week of May | Work-in-progress
Incertech | CFO | West | One-time | Record to Report | Driving closure of accounting for last FY | Ghanisht | 4th Week of May | Work-in-progress | 4th Week of May | Work-in-progress
Incertech | CFO | West | One-time | Record to Report | Improvement and Discipline in accounting processes | Hina |  |  | 4th Week of May | Not Started
Incertech | CFO | West | One-time | Record to Report | Drafting R2R Policies to drive the accounting systems better | Hina |  |  | 4th Week of May | Not Started
Incertech | CFO | West | One-time | Record to Report | Streamlining accounting and MIS systems | Ghanisht |  |  |  |  | 3rd Week of June | Not Started
Incertech | CFO | West | Monthly | Monthly MIS | Introduction of monthly business review deck after aligning on KPIs required to monitor on monthly basis | Ghanisht |  |  |  |  | 4th Week of June | Not Started
Incertech | CFO | West | Monthly | Monthly MIS | Introduction of monthly business review with key stakeholders | Ghanisht |  |  |  |  | 4th Week of June | Not Started
Vervali | CFO | West | One-time | Organisational Goal under Balanced score Card | - From financial perspective | Hina | 1st Week of April | Completed
Vervali | CFO | West | One-time | Organisational Goal under Balanced score Card | - From Customer perspective | Hina | 1st Week of April | Completed
Vervali | CFO | West | One-time | Organisational Goal under Balanced score Card | - From Internal Processes perspective | Hina | 1st Week of April | Completed
Vervali | CFO | West | One-time | Organisational Goal under Balanced score Card | - From Learning & Growth perspective | Hina | 1st Week of April | Completed
Vervali | CFO | West | One-time | Organisational Goal under Balanced score Card | Discussion and finalisation with the Management | Hina | 2nd Week of April | Completed
Vervali | CFO | West | One-time | Annual Operating Plan Implementation | - Set clear and measurable Organisation objective aligned with AOP | Hina | 3rd Week of April | Completed
Vervali | CFO | West | One-time | Annual Operating Plan Implementation | - Communication to the functional heads and alignment with their individual goal sheets | Hina | 3rd Week of April | Completed
Vervali | CFO | West | One-time | Annual Operating Plan Implementation | - Set targets and Budgets for each department and business units | Hina | 4th Week of April | Completed
Vervali | CFO | West | One-time | Annual Operating Plan Implementation | - Allocate Budgets to individual departments | Hina | 4th Week of April | Completed
Vervali | CFO | West | One-time | Annual Operating Plan Implementation | - Align Capability building Budgets with the respective functions | Hina | 4th Week of April | Completed
Vervali | CFO | West | Quarterly | Annual Operating Plan Implementation | - AOP refresh at the end of quarter (if required) | Hina |  |  |  |  | Week 4 | Not Started
Vervali | CFO | West | Monthly | Management Information Systems | Submission of Monthly Business Deck | Hina/Shudhanshu | Week 2 | Completed | Week 2 | Work-in-progress | Week 2 | Not Started
Vervali | CFO | West | Monthly | Management Information Systems | Project Wise Costing and Profitability working | Hina/Shudhanshu | Week 2 | Completed | Week 2 | Work-in-progress | Week 2 | Not Started
Vervali | CFO | West | Monthly | Management Routines Implementation | Fornight Call with the Leadership team with clear actionables | Hina | Week 4 |  | Week 4 |  | Week 4
Vervali | CFO | West | Monthly | Management Routines Implementation | Monthly Review with all functions | Hina |  |  | Week 1 | Completed | Week 1 | Not Started
Vervali | CFO | West | Monthly | Management Routines Implementation | Monthly Business Review | Hina | Week 2 | Completed | Week 2 | Work-in-progress | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Weekly Dashboard Monthly Closing Activity and Performance Review | Weekly Dashboard submission by every Tuesday of nect week | Hina/Shudhanshu/Bala | Every week | Completed | Every week | Work-in-progress | Every week | Not Started
Sl7 | CFO | West | Monthly | Weekly Dashboard Monthly Closing Activity and Performance Review | Drive timely closure of books | Hina/Shudhanshu | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Weekly Dashboard Monthly Closing Activity and Performance Review | Preparation of Monthly Business Review Deck | Hina/Shudhanshu | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Weekly Dashboard Monthly Closing Activity and Performance Review | Monthly Business Review with the founder in the first week of every month | Hina | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Cash Flow and Wealth Management | Monitoring the returns on investment on weekly basis to achieve the target of 8% p.a | Hina | Every week | Completed | Every week | Work-in-progress | Every week | Not Started
Sl7 | CFO | West | Quarterly | Cash Flow and Wealth Management | Quarterly review with the wealth advisor | Hina |  |  | Week 1 | Work-in-progress | Week 1 | Not Started
Sl7 | CFO | West | Monthly | Cash Flow and Wealth Management | Cash flow forecasting and monitoring the collections through weekly cadence calls | Hina | Every week | Completed | Every week | Work-in-progress | Every week | Not Started
Sl7 | CFO | West | Monthly | Compliances | Timely Delivery of Compliance Checklist with Zero Non Compliance on a monthly basis | Hina/Shudhanshu | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Compliances | Accurate calculation and timely payment of advance tax | Hina | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Compliances | US Compliance- Annual and Monthly | Hina | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Financial Processes | Pricing Strategy | Hina |  |  | Week 4 | Not Started
Sl7 | CFO | West | Monthly | Financial Processes | ROI on all marketing spends | Hina/Shudhanshu | Week 2 | Completed | Week 2 | Completed | Week 2 | Not Started
Sl7 | CFO | West | Monthly | Assistance in Zoho Books Finalization and Audit | Assist in Accounting and Book closing | Shudhanshu/Aanand | Every week | Work-in-progress | Every week | Work-in-progress
Sl7 | CFO | West | Monthly | Assistance in Zoho Books Finalization and Audit | Zoho ERP Support | Shudhanshu/Aanand | Every week | Work-in-progress | Every week | Work-in-progress
Sl7 | CFO | West | One-time | Assistance in Zoho Books Finalization and Audit | Audit coordination and Support | Hina/Shudhanshu |  |  | Week 4 | Work-in-progress | Week 4 | Work-in-progress
Balaji Food Products | CFO | East | Quarterly | Inventory optimization | Inventory reconciliation and compiling Non-moving items across multiple units. | Shudhanshu/Hina | Week 1 | Completed
Balaji Food Products | CFO | East | Monthly | Inventory optimization | Monitoring non-moving items across units and implementing disposal procedures along with timelines | Shudhanshu/Hina | Week 2 | Completed | Week1 | Completed | Week 1 | Not Started
Balaji Food Products | CFO | East | Monthly | Monthly MIS Update & deck | Monthly update: PnL, CFS, BS on MoM basis, followed by consolidated MIS. | Shudhanshu/Hina | Week 3 | Completed | Week 3 | Work-in-progress | Week2 | Not Started
Balaji Food Products | CFO | East | Monthly | Monthly MIS Update & deck | Creation of Monthly Performance deck for all units | Shudhanshu/Hina | week 4 | Completed | Week 4 | Not Started | Week2 | Not Started
Balaji Food Products | CFO | East | Monthly | Monthly MIS Update & deck | Monitoring Major KPI, Variance Analysis | Shudhanshu/Hina | Week 4 | Completed | Week 3 | Work-in-progress | Week 2 | Not Started
Balaji Food Products | CFO | East | Monthly | Monthly MIS Update & deck | Reconciliation of outstanding amounts in all the branches. | Shudhanshu/Hina | Week 4 | Completed | Week 3 | Work-in-progress | Week2 | Not Started
Balaji Food Products | CFO | East | One-time | Annual Event | Review of last year's business performance, highlighting constraints with the sales, production, and accounts teams, and proposing a way forward. | Shudhanshu/Hina | Week 3 | Completed
Balaji Food Products | CFO | East | One-time | Annual Event | Drafting meeting minutes and highlighting forward-thinking suggestions. | Shudhanshu/Hina | Week 3 | Completed
Balaji Food Products | CFO | East | One-time | Sales & Production planning and Alignments | Annual Operating Plan (AOP) Discussion with Management | Shudhanshu/Hina |  |  | Week1 | Completed
Balaji Food Products | CFO | East | Quarterly | Sales & Production planning and Alignments | Detailed planning for major SKUs in volume terms for production across all units. | Shudhanshu/Hina |  |  | Week1 | Completed
Balaji Food Products | CFO | East | Quarterly | Sales & Production planning and Alignments | Aligning production with sales targets for each sales region. | Shudhanshu/Hina |  |  | Week2 | Completed
Balaji Food Products | CFO | East | Quarterly | Cash Flow Analysis | Cash Flow Analysis and Discussion for Each Business Unit, along with a Consolidated View for Management Review | Shudhanshu/Hina |  |  | Week2 | Completed
Balaji Food Products | CFO | East | Quarterly | Rolling forecast and AOP Update | Update the Annual Operating Plan (AOP) for each business unit in accordance with the revised sales and production targets for the first and second quarters. | Shudhanshu/Hina |  |  | Week 4 | Work-in-progress
Balaji Food Products | CFO | East | One-time | Petty cash monitoring protocol. | Analyzing significant petty cash outflows and mitigating potential leakages through effective measures. | Shudhanshu/Hina |  |  |  |  | Week 1 | Not Started
Balaji Food Products | CFO | East | One-time | Petty cash monitoring protocol. | Implementing a standardized procedure for cash disbursements and payments within the business. | Shudhanshu/Hina |  |  |  |  | Week 1 | Not Started
Balaji Food Products | CFO | East | One-time | Brand building and marketing analysis. | Analyzing new sales channel of D2C and modern trade sales segment with a cost-benefit analysis for marketing and sales. | Shudhanshu/Hina |  |  |  |  | Week2 | Not Started
Balaji Food Products | CFO | East | One-time | Inventory Management | Updating BoM of Major Products and Contribution Margin workings as per new BoM | Shudhanshu/Hina |  |  | Week4 | Not Started
Balaji Food Products | CFO | East | Monthly | Inventory Management | Implement a weekly update of material issues to production, including weekly adjustments and ensuring Bill of Materials (BoM) accuracy in line with prevailing trends. | Shudhanshu/Hina |  |  | Week 4 | Not Started
Balaji Food Products | CFO | East | Monthly | Inventory Management | Develop Sops for Inventory dispatch procedures | Shudhanshu/Hina |  |  |  |  | Week3 | Not Started
Balaji Food Products | CFO | East | One-time | Cost Optimizations | Conducting a comparative cost analysis and benefits evaluation between bag packaging and carton box packaging. | Shudhanshu/Hina | Week 2 | Completed
Balaji Food Products | CFO | East | Quarterly | Cost Optimizations | Computation of yields at the plant level to optimize and enhance operational efficiency. | Shudhanshu/Hina |  |  |  |  | Week4 | Not Started
Balaji Food Products | CFO | East | Monthly | Cost Optimizations | Closely monitoring major P&L items for effective operational cost reduction. | Shudhanshu/Hina |  |  |  |  | Week4 | Not Started
Balaji Food Products | CFO | East | Monthly | Cost Optimizations | Analyzing slow-moving items at the Ranchi Plant and formulating a production plan based on historical demand patterns. | Shudhanshu/Hina |  |  |  |  | Week4 | Not Started
Crossasyst | CFO | West | One-time | Finalisation of MIS for FY 23-24 and review the same | Drive closure of books | Hina | Week 1 | Completed
Crossasyst | CFO | West | One-time | Finalisation of MIS for FY 23-24 and review the same | Gather all the informations from the account team | Hina | Week 2 | Completed
Crossasyst | CFO | West | One-time | Finalisation of MIS for FY 23-24 and review the same | Create MIS for the FY including PnL, BS and Cash flow | Hina | Week 3 | Completed
Crossasyst | CFO | West | One-time | Finalisation of MIS for FY 23-24 and review the same | Implementation of Record to report SOP | Hina |  |  | Week 2 | Work-in-progress
Crossasyst | CFO | West | Monthly | Management Information Systems | Submission of Monthly Business Deck | Hina |  |  | Week 3 | Work-in-progress
Crossasyst | CFO | West | Monthly | Management Information Systems | Monthly Business Review | Hina |  |  |  |  | Week 1 | Not started
Crossasyst | CFO | West | Monthly | Management Information Systems | Project Wise Costing and Profitability working | Hina |  |  |  |  | Week 3 | Not started
Crossasyst | CFO | West | Monthly | Management Information Systems | Compliance Checklist | Hina |  |  |  |  | Week 1 | Not started
Crossasyst | CFO | West | Weekly | Other Finance related deliverables | Marketing- monitoring the leads and conversion through participation in the calls | Hina |  |  | Week 3 | Not started
Crossasyst | CFO | West | Monthly | Other Finance related deliverables | Monitoring the lost of billing due to leaves and holidays on a monthly basis | Hina |  |  |  |  | Week 1 | Not started
Crossasyst | CFO | West | One-time | Other Finance related deliverables | Finalisation of Incentive for new Sales Head | Hina | Week 1 | Completed

## North (hidden)
| FlipCarbon- CFO ¦Delivery Tracker | [6 empty] | May |  | June |  | July |  | Remarks
| Engagement Name | Engagement Type | Region | Periodicity | Focus Area | Task | Assigned To | Due Date | Status | Due Date | Status | Due Date | Status
| LFT | Business Consulting | North | One-time | Performance Management Process | Final Implementation of PMS and rolling out the PMS policy | Partha | 2024-05-31 | Work-in-progress |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Final Sign off on all Unique R&R and SMART Goals | Partha |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Train employees on SMART Goals based Performance Management | Partha | 2024-06-30 | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time | Implementation of AOP | Finalize the AOP with the appropriate building blocks and assumptions |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Set clear and measurable Organisation objective aligned with AOP |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Communication to the functional heads and alignment with their individual goal sheets |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Set targets and Budgets for each department and business units |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Allocate budgets to individual departments |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Align Capability building budgets with the respective functions |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Continuous Monitoring and review progress |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | AOP refresh at the end of quarter (if required) |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time | Org Structure | Define Reporting lines and Hierarchies | Partha | 2024-05-20 | Work-in-progress |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Facilitate communication on role clarity | Partha | 2024-05-31 | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Ensuring on time issuance of letters | Partha |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Org announcement for approved Org structure and its Implementation | Partha |  | Not Started | 2024-06-20 | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time | Finalizing Airtable for Revenue Tracking | Testing Airtable for Finalizing the model of RTS Data capture including identifying all the pros and cons of Airtable as a revenue management tool to ensure better visibility |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Assess potential limitations or challenges of Airtable, such as scalability issues or integration constraints and Analyze how Airtable's features align with the specific needs of revenue management, considering factors like data visualization and reporting capabilities. |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Compile a comprehensive list of pros and cons based on the evaluation, highlighting key points for decision-making. |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time | RTS Dashboard | Develop the data model required for the RTS dashboard. |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Create mock data and conduct initial testing of the dashboard functionality. |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | One-time |  | Finalize the dashboard design and publish it to stakeholders for feedback. |  |  | Not Started |  | Not Started |  | Not Started
| LFT | Business Consulting | North | Quarterly | Talent Engagement and Communication | Facilitate Quarterly Town Hall | Partha |  | Not Started | 2024-06-28 | Not Started |  | Not Started
| LFT | Business Consulting | North | Monthly |  | Regular Update from CEOs desk | Partha | 2024-05-15 | Work-in-progress | 2024-06-15 | Not Started | 2024-07-15 | Not Started | Will take inputs from Nikita to draft the communique
| LFT | Business Consulting | North | One-time |  | Design and Conduct Employee Engagement Survey for 2024 | Partha |  | Not Started | 2024-06-20 | Not Started |  |  | Need to get the date from Nikita
| LFT | Business Consulting | North | One-time | Competency and Skill Matrix (Optional) | Identify Department wise Behavioral and Functional Skills | Partha | 2024-05-31 | Work-in-progress |  |  |  |  | Initiation in May, completion in June
| LFT | Business Consulting | North | One-time |  | Identify Individual Skill Gap by Gap Analysis | Partha |  | Not Started | 2024-06-30 | Not Started |  |  | Initiation in May, completion in June
| LFT | Business Consulting | North | One-time |  | Competency Framework for FPGA and Software team | Partha |  |  |  | Not Started | 2024-07-31 | Not Started | Initiation in June, completion in July
| LFT | Business Consulting | North | One-time |  | Prepare Skill Matrix for entire organization | Partha |  |  |  | Not Started | 2024-07-31 | Not Started | Initiation in June, completion in July
| LFT | Business Consulting | North | One-time |  | Design Training calendar for 2024-25 | Partha |  | Not Started | 2024-06-30 | Not Started |  |  | Initiation in May, completion in June
| LFT | Business Consulting | North | One-time |  | Monitor Effectiveness of Training plan | Partha |  |  |  | Not Started | 2024-07-31 | Not Started | Initiation in June, completion in July
| LFT | Business Consulting | North | One-time |  | Design L & D Framework for New joiners - alongwith detailed schedule and timeline for completion of initial on the job training | Partha |  |  |  | Not Started | 2024-07-31 |  | Initiation in June, completion in July
| LFT | Business Consulting | North | One-time | Project R&D Sheet-MIS Project Costing Sheet Prepare Project Financial Sheet | Schedule a meeting with ERP vendor to discuss requirements for capturing revenue department-wise data and Provide detailed specifications and data format needed for the customization.
| LFT | Business Consulting | North | One-time |  | Review and approve the proposed solution from the ERP vendor and drive the testing the implemented solution for accuracy and functionality.
| LFT | Business Consulting | North | One-time |  | Arrange a meeting with the GreytHR team to discuss requirements for capturing EOS information And Provide necessary documentation and guidelines for the integration of EOS Data within the system.
| LFT | Business Consulting | North | One-time |  | Review the proposed customization from the GreytHR team
| LFT | Business Consulting | North | One-time |  | Test the implementation to ensure accurate capture of EOS information and provide feedback for adjustments (if any)
| LFT | Business Consulting | North | One-time |  | Documentation of the requirements, specifications, and implementation details should be maintained for future reference and troubleshooting.
| LFT | Business Consulting | North | One-time | Dashboard-Power BI | Data Connection & Transformation: Establish live connections in Power Query for all identified data sources (ERP, EOS Sheet, RTS)
| LFT | Business Consulting | North | One-time |  | Clean & Transform Data: Clean inconsistencies, format data types, and create calculated columns for profitability metrics (Revenue - Salary Cost - R&D Cost).
| LFT | Business Consulting | North | One-time |  | Building the Data Model & Dashboard Design : Define Relationships: Set up relationships between tables in the Power BI data model based on common fields
| LFT | Business Consulting | North | One-time |  | Design Dashboard Layout: Plan the layout for key insights: customer list, revenue, cost & profitability chart, fund flow chart, slicers & filters
| LFT | Business Consulting | North | One-time |  | Create Visuals: Use Power BI visuals to represent data - tables for customer lists, charts for profitability & fund flow trends.
| LFT | Business Consulting | North | One-time |  | Formatting & Branding: Apply consistent formatting throughout the dashboard for a visually appealing presentation aligned with your brand.
| LFT | Business Consulting | North | One-time |  | Test Functionality: Thoroughly test the dashboard for data accuracy, refresh functionality, and proper filtering/slicing behavior.
| LFT | Business Consulting | North | One-time |  | Schedule a review meeting with client stakeholders to assess the effectiveness of the Dashboard
| LFT | Business Consulting | North | One-time |  | Construct Scheduled workflows for automation of data refreshes and reporting for all stakeholders
| LFT | Business Consulting | North | One-time | Talent Management (Optional) | Identify HiPos via 9 Box Grid | Partha | [6 empty] | Optional - Based on the progress of other tasks will check if we can take this up
| LFT | Business Consulting | North | One-time |  | Specialized retention program for Technical personnels | Partha
| LFT | Business Consulting | North | One-time | Grade Designation Matrix (Optional) | Define job levels and criteria | Partha
| LFT | Business Consulting | North | One-time |  | Benchmark Industry data | Partha
| LFT | Business Consulting | North | One-time |  | Validation from stakeholders | LFT
| LFT | Business Consulting | North | One-time |  | Roll-out and communication | Partha
| LFT | Business Consulting | North | One-time | Cashflow forecasting process and management | Forecasting Future cash inflows and outflows accurately
| LFT | Business Consulting | North | One-time |  | Drive the Implementation strategies to manage and optimize cash flow
| LFT | Business Consulting | North | One-time | Develop compliance checklist for the year to avoid penalty | Develop a comprehensive compliance checklist that governs Tax compliance, Regulatory compliance and other financial reporting compliance
| LFT | Business Consulting | North | One-time | Management Routines | Develop the weekly and monthly management routines Templates and drive their implementation
| LFT | Business Consulting | North | One-time | Prepare Finance Data – (Slides to be replaced by Dashboard-Power BI) & Loan Sheet Evaluation | Connect to data sources (RTS, ERP, AOP, Loan Sheet) and clean/transform data.
| LFT | Business Consulting | North | One-time |  | Build data model, define relationships, and design dashboard layout with KPIs, charts, and filters.
| LFT | Business Consulting | North | One-time |  | Create visualizations (line, bar, pie charts) and apply consistent formatting
| LFT | Business Consulting | North | One-time |  | Evaluating the possibilities of whether loan sheet can be automated
| LFT | Business Consulting | North | One-time |  | Identifying the relationship between different variables of the loan sheet
| LFT | Business Consulting | North | One-time |  | Build data model, define relationships, and Incorporating Loan sheet details into the dashboard
| LFT | Business Consulting | North | One-time |  | Test dashboard functionality, deploy to Power BI service or publish for local access.
| LFT | Business Consulting | North | One-time |  | Schedule a review meeting with client stakeholders to assess the effectiveness of the Dashboard
| LFT | Business Consulting | North | One-time |  | Based on the review meeting, refine the dashboard as required
| LFT | Business Consulting | North | One-time |  | Construct Scheduled workflows for automation of data refreshes and reporting for all stakeholders
| LFT | Business Consulting | North | One-time | Define the project costing and profitability process and templates | Estimate project costs with a Cost Estimation Worksheet.
| LFT | Business Consulting | North | One-time |  | Create a Project Budget Template to allocate resources effectively.
| LFT | Business Consulting | North | One-time |  | Use an Expense Tracking Sheet to monitor and control project expenses.
| LFT | Business Consulting | North | One-time |  | Assess project profitability with a Profitability Analysis Report.
| LFT | Business Consulting | North | One-time | GTM Strategy | Understand the market, customers, and competitors through market analysis
| LFT | Business Consulting | North | One-time |  | Define Value Proposition and Identifying the ideal customers .
| LFT | Business Consulting | North | One-time |  | Choosing the right channels and pricing strategy to reach your audience.
| LFT | Business Consulting | North | One-time |  | Develop marketing, sales, and launch plans, measure results, and adjust accordingly
| LFT | Business Consulting | North | One-time | Develop the P2P SOP | Develop a detailed SOP outlining each step of the procure-to-pay process
| LFT | Business Consulting | North | One-time |  | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| LFT | Business Consulting | North | One-time |  | Train employees on the SOP and drive the implement it across the organization.
| LFT | Business Consulting | North | One-time | Develop the R2R SOP | Develop a detailed SOP outlining each step of the record -to- report process
| LFT | Business Consulting | North | One-time |  | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| LFT | Business Consulting | North | One-time |  | Train employees on the SOP and drive the implement it across the organization.
| LFT | Business Consulting | North | One-time | Develop the O2C SOP | Develop a detailed SOP outlining each step of the order to cash process
| LFT | Business Consulting | North | One-time |  | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| LFT | Business Consulting | North | One-time |  | Train employees on the SOP and drive the implement it across the organization.
| LFT | Business Consulting | North | One-time | Develop the DOG SOP | Develop a detailed SOP outlining each step of the delegation of authority process
| LFT | Business Consulting | North | One-time |  | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| LFT | Business Consulting | North | One-time |  | Train employees on the SOP and drive the implement it across the organization.
| LFT | Business Consulting | North | One-time | Quarterly Business Review | Define functional reviews and calendarize them
| LFT | Business Consulting | North | One-time |  | Define the MIS And dashboards to be reviewed by each functions
| LFT | Business Consulting | North | One-time |  | Create actionables and responsibilities out of review
| LFT | Business Consulting | North | One-time |  | Evaluate next quarter's target and make changes if required
| LFT | Business Consulting | North | One-time |  | Communicate the targets to the relevant functions
| LFT | Business Consulting | North | One-time |  | Analyse and communicate the quarterly targets with all functions
Please note:
The data in this template is not real
Due date can be a specific date or end of a particular week
Status is a drop down and a particular status needs to be selected

## Bangalore (hidden)
FlipCarbon- CFO ¦ Delivery Tracker | [6 empty] | May |  | June |  | July
Engagement Name | Engagement Type | Region | Periodicity | Focus Area | Task | Assigned To | Due Date | Status | Due Date | Status | Due Date | Status
InLeather | CFO | South | One-time | Market Research & Competitive Benchmarking | Conducting Deep Dive into Aparell Industry, Competitive Benchmarking for Competitors, Porter's 5 Forces. Industry Benchmarks. Presenting our findings in a detailed White Paper | Bala | 10th May | Completed
InLeather | CFO | South | One-time | Business Model Evaluation | Evaluate the current business model in terms of its effectiveness, scalability, and alignment with market dynamics. Brainstorm with the management on feasibility and scalability of each business model and agree on. Identify potential areas for business model improvement to drive growth and competitiveness future course of action on each business model | Bala | 30th May | Work-in-progress
InLeather | CFO | South | One-time | Annual Operating Plan | Annual Operating Plan, EBITDA Targets, Projected Balance sheet/ P&L, Cashflow Projections | Bhaskar | 30th May | Not Started
InLeather | CFO | South | One-time | Understanding the ERP | Understand and Evaluate how Financial Data is being captured and optimizing the process if needed | Bhaskar | 30th May | Not Started
InLeather | CFO | South | One-time | Profitability Analysis | Analyze the profitability of the business by examining revenue streams, cost structures, and profit margins for each Business Model: 1. For T-base a. Large Retail Format b. MBO, EBO c. Online 2. For FOB: By each brand (Historical margins v/s Present Margin Analysis as well overall profitability) | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Competitive Benchmakring on Key financial ratios like Gross margins, Marketing costs, Other Key costs to drive margin improvement & cost optimization | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Identify factors impacting profitability and explore strategies to enhance it | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Understanding cost centers and revenue drivers Identifying common fixed costs, direct costs attributeable to the 2 lines of business - BU Wise Aligning with management on cost allocation methodologiez for arriving at BU Wise (T-Base) & Brand Wise Profitability ( FOB) | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Developing KPIs that drive deliverables, growth and OKRs | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Evaluate and review capacity utilization trends production line efficiency (if tracked separately) | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Conducting a thorough analysis into given data to understand different financial KPIs, Ratios to dervice insightful analytics & define actionables separately for each business model | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Recommendations of Business continuation & risk management options for each business model | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Understanding the current management systems and review processes and evaluate MIS or data reviewed during the process | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Evaluate and present the feasibility of the individual business models | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Understand how current cashflows are being managed, is there a report, is there cash flow forecasting in place? Is the report standardised? | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Evaluate current cost allocation methods and identify inefficiencies | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Profitability Analysis | Seggregating costs at direct and indirect cost levels. Where direct cost can be drilled down to the prefered granular level | Bhaskar | - | Not Started | 10th June
InLeather | CFO | South | One-time | Cashflow Optimization | Develop a standardized template for reviewing cash flow and ensure its effective implementation. | Bhaskar | 16th May | Work-in-progress
InLeather | CFO | South | One-time | Cashflow Optimization | Identify areas for improvement in cash flow maintenance practices, such as re-negotiating payment terms with vendors, credit terms with custeomrs and inventory. | Bhaskar | 16th May | Work-in-progress
InLeather | CFO | South | One-time | Cashflow Optimization | Perform a detailed inventory analysis to optimize inventory levels and turnover. Evaluate Inventory Ageing. Understanding The seasonal trends in ageing. Work with the management to define an inventory liquidiation plan and great a detailed plan for the same | Bhaskar | 16th May | Work-in-progress
InLeather | CFO | South | One-time | Inventory Liquidation & Analysis | Study and evaluate, improve the current inventory management process to drive a robust inventory management process to eliminate overstocking | Bhaskar | 16th May | Work-in-progress
InLeather | CFO | South | One-time | Inventory Liquidation & Analysis | Establishing Financial Controls, Validating Maker Checker policies in places, Institutionalizing Checks & Balances | Bhaskar | 16th May | Work-in-progress
InLeather | CarbonEye | South | One-time | Data Source Mapping | Conduct interviews with stakeholders to understand current challenges and desired functionalities | Bala | 20th May | Not Started
InLeather | CarbonEye | South | One-time | Data Source Mapping | Identify data sources (ERP, CRM, HRIS, Other Standalone Data Sources). | Bala | 20th May | Not Started
InLeather | CarbonEye | South | One-time | Data Source Mapping | Evaluate the quality, consistency, and level of detail of the data, including aspects like line of business, geographical regions, sales person & product categories, etc | Bala | 20th May | Not Started
InLeather | CarbonEye | South | One-time | Data Source Mapping | Assess the completeness, accuracy, and timeliness of data relevant to profitability metrics | Bala | 20th May | Not Started
InLeather | CarbonEye | South | One-time | Data Source Mapping | Identify data gaps and inconsistencies hindering analysis. | Bala | 20th May | Not Started
InLeather | CarbonEye | South | One-time | Data Source Mapping | Creating a overall data quality assessment report | Bala | 20th May | Not Started
InLeather | CarbonEye | South | One-time | BI Solution Design & Recommendation | Develop a plan to ensure integrity of data going forward | Bala | 20th May | Completed
InLeather | CarbonEye | South | One-time | BI Solution Design & Recommendation | Recommend semi-automated data capture systems to improve data accuracy at the source | Bala | 20th May | Completed
InLeather | CarbonEye | South | One-time | Financial BI Dashboard Design | Providing Profitability dashboards separately for 2 Business Lines. Further broken down in Business units. | Bala | 18th May | Completed
InLeather | CarbonEye | South | One-time | Financial BI Dashboard Design | Working Capital Dashboard which covers Inventory, Receivables and Payables and Which will cover Cash Conversion Cycle for All lines of business, drilled down to Business units | Bala | 18th May | Completed
InLeather | CarbonEye | South | One-time | High-Level Data Governance Plan | Develop a high-level data governance plan outlining key aspects : Data Ownership Data Access Control Data quality standards Data security Measures Data Retention & Archiving | Bala | 17th June | Completed
InLeather | CarbonEye | South | One-time | High-Level Data Governance Plan | Final the Data Governance Plan | Bala | 17th June | Completed
InLeather | CarbonEye | South | One-time | Inventory Dashboard | Creating a dashboard for ageing of inventory based on different lines of business, rolled down to seasonality | Bala | 22nd May | Completed
InLeather | CFO | South | One-time | Discussing & Aligning of future steps | Facilitate discussions with stakeholders to align on future steps and action plans based on the analysis and recommendations provided in the report | Bhaskar | - | Completed | 30th June
InLeather | CFO | South | One-time | Discussing & Aligning of future steps | Compile findings and insights into a comprehensive Diagnosis Report | Deepak | - | Completed | 30th June
Maven Sillicon | CFO | South | One-time | Business Diagnostic | Session with the founders on aspirations and the key challenges | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Diagnostic | Structured / Unstrucrured diagnostics on processes, challenges, issues in each function | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Diagnostic | Creating a buuiness diagnostics report and 180 days plan | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Diagnostic | Report Presentation to the founders | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Deliverables / Goals of CBO | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Advisory on CSR activities | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | ESOP Policy drafting | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | ESOP Policy finalization | Deepak | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Other Deliverables | ESOP Policy Implementation | Deepak | 15th June | Not Started
Maven Sillicon | CFO | South | One-time | Other Deliverables | Advisory on P & L & Balance Sheet - Interest costs and Property trasnfer | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Advisory on CSR compliances and payout | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Advisory on GST complainces and way forward | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Advisory on Directors remuneration | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Advisory on advance tax for Q4 - Fy 2023-24 | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Other Deliverables | Woolf Partnership - MOU, Withholding tax implications, negotiations on fixed costs, alternative commercials arrangements etc | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Strategy & Integration | Discuss, brainstorm and finalize the winning aspiration for the strategy period | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Strategy & Integration | Discuss, brainstorm and finalize the Go to market strategy i.e | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Strategy & Integration | Where to play - Geography, Industry, Customer, channels etc | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Strategy & Integration | How to win in the defined markets | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Strategy & Integration | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Goals & KPI | Identify business critical goals for each financial year in 4 categories : - financial goals, customer goals, business process goals and people development/ capability goals based on the strategy | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Goals & KPI | Identify the critical KPIs to be delivered against each of these goals | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Goals & KPI | Identify timelines for delivery of each of these goals | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Goals & KPI | Align the senior management and founders | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Goals & KPI | Make changes based on the discussion with the founders and senior management | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Business Goals & KPI | Finalize rhe OKRs of Leadership team | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Review the accounting in tally by Account executive for FY 2023-24 and align on next steps i.e. scrap the accounting for FY 2023-24 and start afresh for FY 2024-25 | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Train the accounts executive on accounting concepts | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Train the accounts executive on Tally accounting i.e. chart of accounts, masters, accouting entries for different transactions | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Train the accounts executive on reports and reconciliation | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Review the accounting in Tally every week | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Work with Tally Implementation partner for custimization | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Finalize the scoping of customization and the cost | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Monitor the implementation of customization of tally by the Implementation partner | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Accounting & Tally Training | Review the April reporting from Tally and finalize the April MIS | Gaurav | 31st May | Work-in-progress
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Discuss and align on yearly targets for key financial deliverables i.e. | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Revenue and Gross margins targets for different markets, industry, customer, channels | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Direct costs and other fixed costs in terms of people, tools, technology, marketing, sales based on Org structure defined | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Evaluate and estimate the capex requirements | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Evaluate, estimate and optimize DSO, DPO and other working capital assumptions | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Evaluate funding requirements and define the appropriate capital structure - debt and equity | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Strategic Financial Plan | Deliver the final financial plan | Gaurav | 31st May | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | AOP launch, setting expectations, discussing key people involvement and finalizing the plan and calendar | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | Sharing the formats, data requirement with different functions for data | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | Receipt of details from Client's Team | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | Preparation of AOP | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | First Cut AOP Submission and Discussion | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | Working on required changes after first discussion | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | Finalisation of AOP and presentation | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Annual Operating Plan | Start the implementation & share the finalized KPIs to all functions | Gaurav | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Identifying Competitors | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Consolidate the gathered information, verify the accuracy and reliability of the collected data and conduct reverse searches to cross-verify the information obtained. | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Define specific benchmarks and metrics tailored to the research objectives and ensure that the chosen metrics are relevant and actionable for comparison | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Collecting Financial Data and translating the same in excel for analysis | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Conduct a detailed analysis of the financial statements, including profit and loss statements and balance sheets. Calculate key financial ratios such as profitability metrics (e.g., ROI, ROE, profit margins) | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Analyze the financial data to identify trends and patterns over time and determine the strengths and weaknesses of the competitors based on the financial analysis. | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Compeition Benchmarking | Compile all the collected data, analysis, and insights into a comprehensive competitive benchmarking deck, with key findings, recommendations, and actionable insights for the client. | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Evaluate the current management routines being followed in different functions | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Review the deliverables / Key KPIs for each function | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Basis point no 1 brainstrorm on management routines for each function | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Recommend on weekly / monthly / Quarterly / Annual management routines for each function | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Finalize the management routines and aliso the team for each review | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Create a calendar for the management routines and ensure that calendars of respective team members is blocked for the same | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | Management Routines | Start the management routines | Deepak | - | Completed
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Evaluate the current MIS / data being reviewed by each function | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Review the deliverables / Key KPIs for each function | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Basis point no 1 brainstrorm on the key KPIs/ ratios, deliverables to be reviewed for each function | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Evaluate the current syatems - accounting, MIS, HRMS etc for MIS / data available for the MIS | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Design the templates for different critical MIS - weekly | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Design the templates for different Other MIS - monthly | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Generate the first cut draft weekly MIS with the support of the Maven team | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Generate the first cut draft Monthly MIS with the support of the Maven team | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | MIS & Dashboards | Generate the MIS - weekly and Monthly with the support of Maven team | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | Governance Compliance & Risk Management | Evaluate the status of the current compliances under various statutes | Deepak/Bhaskar | 31st May | Work-in-progress | - | Ongoing
Maven Sillicon | CFO | South | One-time | Governance Compliance & Risk Management | Create a compliance checklist for all the statutory compliances - Direct & Indirect taxes, Companies Act & ROC, FEMA and Payroll compliances | Deepak/Bhaskar | 31st May | Work-in-progress | - | Ongoing
Maven Sillicon | CFO | South | One-time | Governance Compliance & Risk Management | Familarise the HR & Finance team with the compliance checklist and support them to update the same | Deepak/Bhaskar | 31st May | Work-in-progress | - | Ongoing
Maven Sillicon | CFO | South | One-time | Governance Compliance & Risk Management | Audit the first checklist updated by the team - for the month of April | Deepak/Bhaskar | 31st May | Work-in-progress | - | Ongoing
Maven Sillicon | CFO | South | One-time | Governance Compliance & Risk Management | Review the checklist every month, to be completed by 25th of the ensuing month with Maven team | Deepak/Bhaskar | 31st May | Work-in-progress | - | Ongoing
Maven Sillicon | CFO | South | One-time | Governance Compliance & Risk Management | Quarterly review of the compliances checklist with the Management | Deepak/Bhaskar | 31st May | Work-in-progress | - | Ongoing
Maven Sillicon | CFO | South | One-time | Annual Business Review | Define functional reviews and calendarize them | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Annual Business Review | Define the MIS and dashboards to be reviewed by each functions | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Annual Business Review | Conduct the reviews as per the calendar with each function | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Annual Business Review | Create actionables and responsibilities out of review | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Annual Business Review | Evaluate next quarter's target and make changes if required | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Annual Business Review | Communicate the targets to the relevant functions | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Annual Business Review | Analyse and communicate the quarterly targets with all functions | Deepak/Bhaskar | 31st May | Not Started | -
Maven Sillicon | CFO | South | One-time | Digital Transformation Guidance | Evaluate the critical processes in each function which needs to be automated | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | Digital Transformation Guidance | Evaluate whether such processes can be automated | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | Digital Transformation Guidance | Research on the tools, platforms available for automating the critical processes alongwith the cost implications | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | One-time | Digital Transformation Guidance | Advise on priortization based on cost and criticality | Deepak/Bhaskar | - | Not Started | 30th June
Maven Sillicon | CFO | South | Monthly | Monthly Performance Review | Performance of all functions for the month and YTD | Gaurav | 31st May | Work-in-progress | -
Agriplast | CFO | South | One-time | Financial Process Review | Financial Forecast launch, setting expectations, discussing key people involvement and finalizing the plan and calendar | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Process Review | Sharing the formats, data requirement with different functions for data | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Process Review | Receipt of details from Client's Team | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Process Review | Preparation of Financial Forecast | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Process Review | First Cut Finnacial Forecast Submission and Discussion | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Process Review | Finalize the AOP with the required changes after first discussion | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Process Review | Start the implementation & share the finalized KPIs to all functions | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | Financial Forecast launch, setting expectations, discussing key people involvement and finalizing the plan and calendar | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | Sharing the formats, data requirement with different functions for data | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | Receipt of details from Client's Team | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | Preparation of Financial Forecast | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | First Cut Finnacial Forecast Submission and Discussion | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | Finalize the AOP with the required changes after first discussion | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Financial Forecast | Start the implementation & share the finalized KPIs to all functions | Gaurav | - | Completed | -
Agriplast | CFO | South | One-time | Annual Operating Plan | AOP launch, setting expectations, discussing key people involvement and finalizing the plan and calendar | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | Sharing the formats, data requirement with different functions for data | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | Receipt of details from Client's Team | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | Preparation of AOP | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | First Cut AOP Submission and Discussion | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | Working on required changes after first discussion | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | Finalisation of AOP and presentation | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Annual Operating Plan | Start the implementation & share the finalized KPIs to all functions | Gaurav | 17th May | Work-in-progress
Agriplast | CFO | South | One-time | Detailed Finance Diagnostics | Session with the Key Management Team (KMT) on finance related challenges & expectations | Bhaskar | 31st May
Agriplast | CFO | South | One-time | Detailed Finance Diagnostics | Structured / Unstructured diagnostics on Internal controls,SOPs, MIS, key challenges, issues in finance function | Bhaskar | 31st May
Agriplast | CFO | South | One-time | Detailed Finance Diagnostics | Review and analyse existing Financials for growth tends and key financial ratios | Bhaskar | 31st May
Agriplast | CFO | South | One-time | Detailed Finance Diagnostics | Conduct the Finance baseline assessment along with Finance team and highlight gap areas if any | Bhaskar | 31st May
Agriplast | CFO | South | One-time | Detailed Finance Diagnostics | Creating a business diagnostics report based on the findings | Bhaskar | 31st May
Agriplast | CFO | South | One-time | Detailed Finance Diagnostics | Report presentation to the founders | Bhaskar | 31st May
Agriplast | CFO | South | One-time | Procure to Pay SOP | Review the current process (documented / undocument) of procure to pay from the Procurement team, Stores / warehouse team and Finance team | 31st May
Agriplast | CFO | South | One-time | Procure to Pay SOP | Evaluate the process for financial controls i.e. segregation of duties, maker, checker control, reconciliation control et all | 31st May
Agriplast | CFO | South | One-time | Procure to Pay SOP | Identify the gaps and script the revised SOP with deliverables defined for each function involved | 31st May
Agriplast | CFO | South | One-time | Procure to Pay SOP | Share the draft SOP with the management team for approval / feedback | 31st May
Agriplast | CFO | South | One-time | Procure to Pay SOP | Share the final SOP post incoporating the feedback received from the management | 31st May
Agriplast | CFO | South | One-time | Procure to Pay SOP | Implement the SOP with the support of Procurement, stores / warehouse and finance team | 31st May
Agriplast | CFO | South | One-time | Order to Cash SOP | Review the current process (documented / undocument) of Order to Cash from the Sales / Post salest team, Stores / warehouse team and Finance team | 30th June
Agriplast | CFO | South | One-time | Order to Cash SOP | Evaluate the process for financial controls i.e. segregation of duties, maker, checker control, reconciliation control et all | 30th June
Agriplast | CFO | South | One-time | Order to Cash SOP | Identify the gaps and script the revised SOP with deliverables defined for each function involved | 30th June
Agriplast | CFO | South | One-time | Order to Cash SOP | Share the draft SOP with the management team for approval / feedback | 30th June
Agriplast | CFO | South | One-time | Order to Cash SOP | Share the final SOP post incoporating the feedback received from the management | 30th June
Agriplast | CFO | South | One-time | Order to Cash SOP | Implement the SOP with the support of Sales / Post salest team, Stores / warehouse team and Finance team | 30th June
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Understand the current process on cashflow management and forecast. How is the forecast created ? Is it weekly, monthly?
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Share the format for cashflow forecast, data requirement with different functions for data (Weekly, monthly)
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Train the finance team on creation of Cash flow forecasts and more importantly manage the cashflows on weekly basis
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Monitor the cashflows on a weekly, monthly basis for improvement in net cashflow
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Montior the actauls vs forecast on a weekly basis to improve the forecasts
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Ensure the periodic surplus funds are invested in funds / FDs
Agriplast | CFO | South | One-time | Cashflow forecast and Wealth Management | Monitor the returns from the surplus funds invested every month
Agriplast | CFO | South | One-time | Compliance Management | Customize the compliances checklist based on the compliances to be done & monitored periodically. Share the same with Finance Team
Agriplast | CFO | South | One-time | Compliance Management | Finalize the checklist based on feedback from the Finance Team
Agriplast | CFO | South | One-time | Compliance Management | Ensure that the checklist is updated everymonth before the payment and filing due dats
Agriplast | CFO | South | One-time | Compliance Management | The udpated checklist is reveiwed every month with the Finance team
Agriplast | CFO | South | One-time | Compliance Management | Once a quarter review with the management onstatus of complainces for the last quarter
Agriplast | CFO | South | One-time | Compliance Management | Incase of any delays or defaults, define actionables to ensure no delays or defaults in the future
Agriplast | CFO | South | One-time | Record to Report SOP | Review the current process (documented / undocument) of record to report process with the Finance Team | 31st July
Agriplast | CFO | South | One-time | Record to Report SOP | Evaluate the process for financial controls i.e. segregation of duties, maker, checker control, reconciliation control et all | 31st July
Agriplast | CFO | South | One-time | Record to Report SOP | Identify the gaps and script the revised SOP with deliverables defined for each function involved | 31st July
Agriplast | CFO | South | One-time | Record to Report SOP | Share the draft SOP with the management team for approval / feedback | 31st July
Agriplast | CFO | South | One-time | Record to Report SOP | Share the final SOP post incoporating the feedback received from the management | 31st July
Agriplast | CFO | South | One-time | Record to Report SOP | Implement the SOP with the support of Sales / Post salest team, Stores / warehouse team and Finance team | 31st July
Agriplast | CFO | South | One-time | Record to Report SOP | Create a month end closing checklist to ensure accurate MIS for each month from SAP | 31st July
Agriplast | CFO | South | One-time | Monthly Performance Review | Monthly and YTD financial performance review
Agriplast | CFO | South | One-time

## Chennai (hidden)
FlipCarbon- CFO ¦Delivery Tracker | [6 empty] | May |  | June |  | July |  | Remarks
Engagement Name | Engagement Type | Region | Periodicity | Focus Area | Task | Assigned To | Due Date | Status | Due Date | Status | Due Date | Status
VC Nutri Foods | CFO Services | South | One-time | AOP Preparation, Review and Completion | AOP launch, setting expectations, discussing key people involvement and finalizing the plan | Murali Krishna | 2024-05-01 | Completed |  | Completed
VC Nutri Foods | CFO Services | South | One-time |  | Sharing the formats, data requirement with different functions for data |  | 2024-05-01 | Completed |  | Completed
VC Nutri Foods | CFO Services | South | One-time |  | Sending list of Required Details in the particular format |  | 2024-05-01 | Completed |  | Completed
VC Nutri Foods | CFO Services | South | One-time |  | Receipt of details from Client's team |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time |  | Preparation of AOP |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time |  | First Cut AOP Submission and Discussion |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time |  | Working on required changes after first discussion |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time |  | Finalisation of AOP |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time |  | Final Presentation |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time |  | Implementation plan |  | 2024-05-01 | Client Info Pending |  | Client Info Pending
VC Nutri Foods | CFO Services | South | One-time | Articulation of Business Critical Goals / KPIs | Identify business critical goals for the year | Murali Krishna | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | One-time |  | Identify the critical KPIs to be delivered against each of these goals |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | One-time |  | Identify timelines for delivery of each of these goals |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | One-time |  | Align the senior management and founders |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | One-time |  | Make changes based on the discussion with the founders and senior management |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | One-time |  | Finalise the goals and start the implementation process |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly | Cash Flow Forecasting & Management | Cash Flow forecasting and management |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Template for Weekly and Monthly Cash flow forecasting and management |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Cash flow forecasting (to anticipate any potential shortfalls or surpluses) |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Track the actual cash inflow and outflow against the forecasted no. |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Align and Fix payment days for vendors, salary and reimbursement |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Review the payment terms with vendor and suggest improvements |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Receivable management through well defined follow up system and process |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Advise on effectively managing cashflow shortfalls and excess |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Three months rolling cash flow forecast every month |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly | Monthly P&L Process | Review current Monthly P&L process |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Ensure Cut Off Dates for Month Closing |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Ensure Month End Provisioning for all unbooked bills/expenses |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | All Production Orders are confirmed by month end ensure material consumption accounting |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Month End Physical Verification for FG, SFG and RMPM Inventory |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Monthly P&L Closure and Output |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | P&L Analysis, insights and action plans |  | 2024-05-01 | Not Started |  | Not Started
VC Nutri Foods | CFO Services | South | Monthly |  | Sustain Monthly & YTD P&L process |  | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time | AOP Preparation, Review and Completion | AOP launch, setting expectations, discussing key people involvement and finalizing the plan | Murali Krishna | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Sharing the formats, data requirement with different functions for data |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Sending list of Required Details in the particular format |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Receipt of details from Client's team |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Preparation of AOP |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | First Cut AOP Submission and Discussion |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Working on required changes after first discussion |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Finalisation of AOP |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Final Presentation |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time |  | Implementation plan |  | 2024-04-01 | Completed |  | Completed
Kamala Farms | CFO Services | South | One-time | Articulation of Business Critical Goals / KPIs | Identify business critical goals for the year | Murali Krishna | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Identify the critical KPIs to be delivered against each of these goals |  | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Identify timelines for delivery of each of these goals |  | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Align the senior management and founders |  | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Make changes based on the discussion with the founders and senior management |  | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Finalise the goals and start the implementation process |  | 2024-05-01 | Not Started |  | Not Started
Kamala Farms | CFO Services | South | One-time | Extraction Plant Readiness | Prepare Tracker for all the requirements |  | 2024-04-01 | Completed |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Follow up on required licenses for setting up the plant |  | 2024-05-01 | Client Info Pending |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | GST Registration |  | 2024-05-01 | Client Info Pending |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Follow up on bank loan sanction |  | 2024-05-01 | Client Info Pending |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Track Procurement of Plant & Machinery required and Installation |  | 2024-05-01 | Client Info Pending |  | Not Started
Kamala Farms | CFO Services | South | One-time |  | Procurement of Input Materials and Initial sample batches for commercial clearance |  |  |  | 2024-06-01 | Not Started
Kamala Farms | CFO Services | South | One-time |  | ROI Working |  | 2024-04-01 | Completed |  | Not Started
Kamala Farms | CFO Services | South | One-time | Essential Oils Readiness | Prepare Tracker for all the requirements |  | 2024-04-01 | Completed
Kamala Farms | CFO Services | South | One-time |  | Follow up on required licenses for setting up trading |  | 2024-04-01 | Completed
Kamala Farms | CFO Services | South | One-time |  | GST Registration |  | 2024-04-01 | Completed
Kamala Farms | CFO Services | South | One-time |  | Amazon Listing |  | 2024-04-01 | Client Info Pending
Kamala Farms | CFO Services | South | One-time |  | Track Procurement of purchases |  | 2024-04-01 | Client Info Pending
Kamala Farms | CFO Services | South | One-time |  | Review and Finalise the pricing |  | 2024-04-01 | Client Info Pending
Kamala Farms | CFO Services | South | One-time |  | ROI Working |  | 2024-04-01 | Completed
NAR Samruddi | CFO Services | South | One-time | Feasibility study of fractional investment | Analyze the demand for fractional ownership in commercial real estate. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Understand & ascertain the regulatory landscape governing fractional ownership in real estate, especially in TN. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Evaluate the availability of technology infrastructure for secure transactions, transparent reporting, and a user-friendly experience. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Develop legal frameworks, property valuation methods, and contingency plans for unforeseen events. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Consider the liquidity of the investment wrt the potential challenges associated with liquidity in the real estate market. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Focus on creating an intuitive and user-friendly platform. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Due Diligence in terms of Transparency in property details, financials, and potential risks is crucial for building trust among investors. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Process for establishing for strong partnerships with stakeholders can contribute to a diverse and attractive portfolio for potential investors. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Provide clear exit strategies for investors, including options to sell their fractional shares or exit the investment at predefined intervals. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Analyze existing and potential competitors in the market. Differentiation and innovation will be essential to stand out in a competitive landscape. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time |  | Consider the economic climate and its impact on commercial real estate. Economic downturns or uncertainties can affect property values and rental incomes. |  | 2024-04-01 | Not Started
NAR Samruddi | CFO Services | South | One-time | Budgeting/ AOP | Review of 23-24 and finalization of Budgeting for 24-25 |  | 2024-04-01 | Client Info Pending
DAC DEVELOPERS | Business Consulting | South | One-time | GIO Goals and AOP Reviews & Completion | AOP launch, setting expectations, discussing key people involvement and finalizing the plan | Murali Krishna for AOP & Org.Goals and Sukanya for GIO Goals | 2024-04-01 | Completed
DAC DEVELOPERS | Business Consulting | South | One-time |  | Sharing the formats, data requirement with different functions for data |  | 2024-04-01 | Completed
DAC DEVELOPERS | Business Consulting | South | One-time |  | Sending list of Required Details in the particular format |  | 2024-04-01 | Completed
DAC DEVELOPERS | Business Consulting | South | One-time |  | Receipt of details from Client's team |  | 2024-04-01 | Client Info Pending
DAC DEVELOPERS | Business Consulting | South | One-time |  | Preparation of AOP |  | 2024-05-01 | Work-in-progress
DAC DEVELOPERS | Business Consulting | South | One-time |  | First Cut AOP Submission and Discussion |  | 2024-05-01 | Work-in-progress
DAC DEVELOPERS | Business Consulting | South | One-time |  | Working on required changes after first discussion |  | 2024-05-01 | Work-in-progress
DAC DEVELOPERS | Business Consulting | South | One-time |  | Finalisation of AOP |  | 2024-05-01 | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Final Presentation |  | 2024-05-01 | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Implementation plan |  | 2024-05-01 | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time | Working Groups & Committees | Review the current processes how decisions are taken currently; Land purchase, Design & Structural, Vendors appointment for Material Supplies, Marketing Services and Other Admin Services, Project Scheduling, IT H/W & S/W Purchases, etc. | Murali Krishna | May to July Period | Not Started | May to July Period | Not Started | May to July Period | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Identify the gaps if any in the current processes for informed decision making |  |  | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Define which are all functions must be involved in decision making for each such activity |  |  | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Form separate work group committes for each such activity |  |  | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Define the process of decision making by the committee |  |  | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Align all stake holders including top management on the WC process |  |  | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Monitor the implementation through periodic internal review |  |  | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time | Finance & Purchase SOP | Align the respective team with the draft SOP | Murali Krishna | 2024-04-01 | Work-in-progress |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Finalize the SOP after feedback from all stakeholders |  | 2024-04-01 | Work-in-progress |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Share the SOP with the respective functions for implementation |  | 2024-04-01 | Work-in-progress |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Monitor the implementation through periodicreview of internal audit plans and reports |  | 2024-04-01 | Work-in-progress |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time | Construction Site Processes | Awaiting Engineering SVP feedback/inputs | Murali Krishna | 2024-04-01 | Client Info Pending |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time |  | Roll out to Site Teams |  | 2024-04-01 | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time | SFP-3Y Period | Strategic Financial Plan for the 3Y Period - To realign with the client | Murali Krishna | Jun - July | Not Started |  | Not Started |  | Not Started
DAC DEVELOPERS | Business Consulting | South | One-time
DAC DEVELOPERS | Business Consulting | South | One-time
DAC DEVELOPERS | Business Consulting | South | One-time
Please note:
The data in this template is not real
Due date can be a specific date or end of a particular week
Status is a drop down and a particular status needs to be selected