## Sheet1
Task | Duration | Substeps | Due Date
Revision on the Loadmaster Dashboard | 10 days | 1. Review current insights and identify areas for improvement. (2 days) 2. Gather feedback from stakeholders on desired changes. (2 days) 3. Implement revisions based on feedback. (5 days) 4. Test dashboard functionality and accuracy. (1 day) | 2024-03-16
Creating the Global Customer Service Dashboards | 10 days | 1. Define the specific metrics and KPIs to be included. (2 days) 2. Gather necessary data sources for customer service analytics. (3 days) 3. Design the dashboard layout and visualization. (3 days) 4. Develop the dashboard prototype. (2 days) | 2024-03-29
Connecting with the Team for Queries | Ongoing | Schedule regular check-ins with the team to address any questions or concerns. (Daily or as needed)
Presenting the Aligned Mockup to Stakeholders | 5 days | 1. Prepare a presentation outlining the mockup changes and enhancements. (2 days) 2. Schedule a meeting with stakeholders to present the mockup. (1 day) 3. Gather feedback and address any concerns. (2 days)
Understanding Data Sources | 5 days | 1. Identify and document all data sources related to master airway bills and house airway bills. (2 days) 2. Analyze the structure and format of each data source. (2 days) 3. Verify data accuracy and integrity. (1 day)
Understanding Present Reporting Needs | 5 days | 1. Interview key stakeholders to understand current reporting requirements. (2 days) 2. Analyze existing reports and their effectiveness. (2 days) 3. Document the findings and identify gaps or areas for improvement. (1 day)
Developing a Comprehensive Plan for Report Delivery | 5 days | 1. Review data gathered from tasks 5 and 6. (1 day) 2. Define phases for report delivery based on priorities and resources. (2 days) 3. Develop a timeline for each phase of report delivery. (2 days)